## Cover
Alayans
Meeting Room Booking System
WBS Estimate
Revision No. : | 1
Modified By – Date : | Alba, Angela Monique - 2024/08/25
Preliminary Review and Approval – Date : | Santella, Tomas Emmanuel - yyyy/mm/dd
Final Review and Approval – Date : | Santella, Tomas Emmanuel - yyyy/mm/dd

## Revision History
|  | REVISION HISTORY |  | REVISION HISTORY
REV NO | MODIFIED BY |  | MODIFIED DATE |  | REMARKS | PRELIMINARY REVIEW AND APPROVAL | DATE REVIEWED | FINAL REVIEW AND APPROVAL | DATE APPROVED
1 | Alba, Angela Monique |  | 2024-08-27 |  | Initial Creation | Santella, Tomas Emmanuel | yyyy/mm/dd | Santella, Tomas Emmanuel | yyyy/mm/dd

## Function List
MODULE | FUNCTION / DESCRIPTION / ASSUMPTIONS | Type | FUNCTIONAL CATEGORY |  |  |  |  | Estimate (MD) | Remarks
|  |  | SCREEN | REPORT | BATCH | OTHERS
Meeting Room Booking System
User Management
Add User | Allows admins to add new users with details like: Name Email Password | Web | x |  |  |  |  | 2
Edit User | Lets admins update user details, such as: Email Reset Password | Web | x |  |  |  |  | 1
Delete User | Allows admins to remove users from the system entirely. | Web | x |  |  |  |  | 1
View Users | Displays a list of users along with their details. | Web | x |  |  |  |  | 1
Account Management
Add Account | Allows superadmins to add new accounts with details like: Name Email Role (Admin/User) Password | Web | x |  |  |  |  | 3
Edit Account | Lets superadmins update user details, such as: Change Role Email Reset Password | Web | x |  |  |  |  | 2
Delete Account | Allows admins to remove users from the system entirely. | Web | x |  |  |  |  | 2
View Accounts | Displays a list of users along with their details and roles. | Web | x |  |  |  |  | 2
User Authentication
Login | Validates user credentials and establishes a session or JWT token for authentication. | Web | x |  |  |  |  | 4
Logout | Ends the user's session or token, logging them out of the system and redirects to the login page. | Web | x |  |  |  |  | 2
Admin Room Management
Add Room | Admins can add new rooms with details like: Name Location Capacity Facilities | Web | x |  |  |  |  | 1
Edit Room | Enables administrators to update room details in the database | Web | x |  |  |  |  | 1
Delete Room | Allows administrators to remove meeting rooms from the database | Web | x |  |  |  |  | 1
View Rooms | Displays a list of all meeting rooms. | Web | x |  |  |  |  | 1
Booking Management
Create Booking | Allows users to book a room by selecting the: Room Date Time Duration | Web | x |  |  |  |  | 1
Edit Booking | Enables users to modify their existing bookings. | Web | x |  |  |  |  | 1
Delete Booking | Allows users to cancel their room bookings. | Web | x |  |  |  |  | 1
View Bookings | Displays a list of all bookings with options to filter by room, date, and user. | Web | x |  |  |  |  | 1
User Recurring Bookings Management
Create Recurring Booking | Enables users to create bookings that repeat at specified intervals, such as daily or weekly. | Web | x |  |  |  |  | 1
Edit Recurring Booking | Allows users to modify their recurring bookings. | Web | x |  |  |  |  | 1
Cancel Recurring Booking | Lets users cancel their recurring bookings entirely. | Web | x |  |  |  |  | 1
Notifications
Booking Notifications | Sends notifications to users upon booking creation, updates, and cancellations. | Web | x |  |  |  |  | 3
Reminder Notifications | Sends reminders to users before their bookings start. | Web | x |  |  |  |  | 2
Reporting & Analytics
Booking Summary | Summarizes booking data by: Room Date User | Web | x |  |  |  |  | 2
Room Usage Report | Generates reports on: Room usage Total bookings Peak usage times User activity | Web | x |  |  |  |  | 4
Setting and Preferences
Set Preferences | Allows users to set personal preferences, such as notification settings and default booking duration. | Web | x |  |  |  |  | 2
Calendar Integration
View Calendar | Integrates with external calendars (e.g., Outlook, Google Calendar) to display bookings and allows direct room booking from calendars. | Web | x |  |  |  |  | 4
Overall
[7 empty] | MD | 48
[7 empty] | MM | 2.4

## Jumpstart Program Schedule
Alba | Booc | Lazarte | Miñoza | Sagnoy | WBS | Task | Baseline Start | Baseline End | Days | Predecessors | actual days data | Actual Start | Actual End
[5 empty] | 1 | Meeting Room Booking System |  |  |  |  | 1
[5 empty] | 2 | Account Management |  |  |  |  | 1
[5 empty] | 3 | Add Account | Sept 23, 2024 | Sept 25, 2024 | 3 |  | #VALUE!
[5 empty] | 4 | Edit Account | Sept 26, 2024 | Sept 27, 2024 | 2 |  | #VALUE!
[5 empty] | 5 | Delete Account | Sept 30, 2024 | 2024-10-01 | 2 |  | #VALUE!
[5 empty] | 6 | View Account | 2024-10-02 | 2024-10-03 | 2 |  | 2
[5 empty] | 7 | User Management
[5 empty] | 8 | Add User | Sept 26, 2024 | Sept 27, 2024 | 2 | 3 |  |  |  | Holidays
[5 empty] | 9 | Edit User | Sept 30, 2024 | Sept 30, 2024 | 1 | 4 |  |  |  | 2024-11-01 | Friday | All Saints' Day | Special Non-working Holiday
[5 empty] | 10 | Delete User | 2024-10-02 | 2024-10-02 | 1 | 5 |  |  |  | 2024-11-02 | Saturday | All Souls' Day | Special Non-working Holiday
[5 empty] | 11 | View User | 2024-10-04 | 2024-10-04 | 1 | 6 |  |  |  | 2024-11-30 | Saturday | Bonifacio Day | Regular Holiday
[5 empty] | 12 | User Authentication |  |  |  |  | 1
[5 empty] | 13 | Login | Sept 23, 2024 | Sept 26, 2024 | 4 |  | #VALUE! |  |  | Mandays per Dev
[5 empty] | 14 | Logout | Sept 27, 2024 | Sept 30, 2024 | 2 |  | #VALUE! |  |  | Alba = 6 mandays
[5 empty] | 15 | Admin Room Management |  |  |  |  | 1 |  |  | Booc = 7 mandays
[5 empty] | 16 | Add Room | 2024-10-01 | 2024-10-01 | 1 |  | 1 |  |  | Lazarte = 9 mandays
[5 empty] | 17 | Edit Room | 2024-10-02 | 2024-10-02 | 1 | 16 | 1 |  |  | Minoza = 10 mandays
[5 empty] | 18 | Delete Room | 2024-10-03 | 2024-10-03 | 1 | 17 | 1 |  |  | Sagnoy = 10 mandays
[5 empty] | 19 | View Rooms | 2024-10-04 | 2024-10-04 | 1 | 18 | 1 |  |  | Baseline Start -> Baseline End = Sept 23 -> Oct 11 = 21days
[5 empty] | 20 | Booking Management/Recurring Booking |  |  |  |  | 1
[5 empty] | 21 | Create Booking/Recurring Booking | Sept 23, 2024 | Sept 23, 2024 | 1 |  | #VALUE!
[5 empty] | 22 | Edit Booking | Sept 24, 2024 | Sept 24, 2024 | 1 | 21 | #VALUE!
[5 empty] | 23 | Delete Booking | Sept 25, 2024 | Sept 25, 2024 | 1 | 22 | #VALUE!
[5 empty] | 24 | View Booking | Sept 26, 2024 | Sept 26, 2024 | 1 | 23 | #VALUE!
[5 empty] | 29 | Notifications |  |  |  |  | 1
[5 empty] | 30 | Booking Notifications | Sept 27, 2024 | 2024-10-01 | 3 | 21 | #VALUE!
[5 empty] | 31 | Reminder Notifications | 2024-10-02 | 2024-10-03 | 2 | 30 | 2
[5 empty] | 32 | Reporting & Analytics |  |  |  |  | 1
[5 empty] | 33 | Booking Summary | 2024-10-04 | 2024-10-07 | 2 | 21 | 4
[5 empty] | 34 | Room Usage Report | 2024-10-08 | 2024-10-11 | 4 | 33 | 4
[5 empty] | 35 | Setting and Preferences |  |  |  |  | 1
[5 empty] | 36 | Set Preferences | 2024-10-04 | 2024-10-07 | 2 |  | 4
[5 empty] | 37 | Calendar Integration |  |  |  |  | 1
[5 empty] | 38 | View Calendar | Sept 30, 2024 | 2024-10-03 | 4 |  | #VALUE!

## Summary (hidden)
Project Name |  |  |  | Alayans - Meeting Room Booking System
Date |  |  |  | 2019-09-05
[7 empty] | MD Effort | MM Effort | REMARKS
|  | Project Management |  |  |  |  | #REF! | #REF! | Shared PM
|  | Design (HLD, LLD, UX) |  |  |  |  | #REF! | #REF! | Dedicated Developer
|  | Development, Unit Test |  |  |  |  | #REF! | #REF! | Dedicated Developer
|  | Application Testing |  |  |  |  | #REF! | #REF! | Dedicated Developer
|  | Post Implementation | [6 empty] | Dedicated Developer
|  | Staging Release + UAT Support |  |  |  |  | #REF! | #REF!
|  | Production Release + Hypercare Support |  |  |  |  | #REF! | #REF!
[7 empty] | #REF! | #REF!
Project Description
[Project Description]
Scope of Development/ Assumptions
- | Please refer to the function list. Estimate is entirely based on the function list.
If additional scope will be included, it will be treated as a separate estimate.
- | If requirements will change through the course of development, it will be re-assessed on a per need basis.
- | If overall schedule will be impacted due to major changes, Alliance will inform Client.
- | If Applicable, all licensed 3rd Party API Integration will be c/o client.
- | For integrations, it is assumed that the 3rd Party already has an available API that will be used to fetch/send data between systems.
- | All copyright images and text to be used in the website shall be provided by client.
Environment:
Language/s to be supported
|  | x | English
Others. Please specify:
Accessibility
|  | x | Intranet
Internet
Development Environment (if there is a preference)
OS Information:
Technologies to be Used:
Programming Language/s:
Web / APIs
[5 empty] | Front End | :
[5 empty] | Back End | :
[5 empty] | IDE | :
[5 empty] | DB | :
Mobile
[5 empty] | Front End | :
[5 empty] | IDE | :
Browser Support
|  | x | Chrome |  | Version/s:
|  | x | Firefox |  | Version/s:
|  |  | IE |  | Version/s:
|  |  | Safari |  | Version/s:
Mobile Browser Support
|  | x | Yes
No
Mobile Support
|  |  | iOS |  | Version/s:
|  | x | Android |  | Version/s:
|  |  | Windows |  | Version/s:
Hardware/Software/Servers
| - | Alliance provides standard workstations. Beyond this or licenses very specific to the project requirements, client will provide the
necessary software licenses (if any / as applicable) to Alliance on a consignment basis.
| - | Client will provide the Staging and Production server / environment.
Deployment:
|  | x | Staging
|  |  | x | c/o Alliance
c/o Client
|  | x | Production
|  |  | x | c/o Alliance
c/o Client
Deliverables:
|  | x | High Level Design Document/ Functional Specs Document
|  | x | Source Code
|  | x | Database
|  | x | Quality Report/ Test Results
Proof of Tests
User Manual
|  | x | Release Checklist
Others, Pls indicate:
Testing:
Will test only on the selected browsers (web and/or mobile):
|  | x | Unit Test
|  | x | Integration / System Test
|  | x | Performance Test
|  | x | Security Test
Mobile Test Devices
| - | If client provides handset for testing, actual handset will be used during testing.
| - | If the handset commonly used by the client is available, then testing will be done using the actual handset.
Else, testing will be done via emulator.
Browser:
| - | Will use Google Chrome during testing.
Process:
Waterfall
|  | x | Agile/ Hybrid
Client Process
Communication
| - | Client will assign 1 focal person who will act as product owner and will help form/confirm the requirements.
| - | Regular meeting will be conducted between Client Product Owner and DEV Team.
| - | Tool for regular meeting can be through Zoom (preferred videoconferencing tool).
| - | Time of Regular meeting can be agreed upon both by Client Product Owner and DEV Team.

## Function List Guide (hidden)
MODULE | FUNCTION | DESCRIPTION/ DETAILS | FUNCTIONAL CATEGORY |  |  |  | ACCESS RIGHTS |  | Estimate (MD) | REMARKS
|  |  | SCREEN | REPORT | BATCH | OTHERS | ADMIN | NORMAL
USER INTERFACE/ DESIGN
Layout Theme
Color palette
Logo/s
Font Style
Font Size
Screen Resolution
LOGIN
Login/Logout/Clear Fields
Forgot Password
Change password
HOME PAGE
Dashboard
Dashlets
Navigation Pane
CRUD/ MASTER/ TRANSACTIONAL MODULE
Main Module
Search / List View
Add Entry
Mass Upload
Modify
Detailed View
Delete
Duplicate Copy
OTHERS:
SubPanel/ Section
List Section
Add Section
Edit Section
View Section
Delete Section
Action Buttons
Save
Submit
Cancel
Close
Approve
Reject
Feedback
Search Facility
Global Search
Like Search
Searchable Dropdowns
Predictive Search
WORKFLOW
Request Workflow
Approve (multiple approvers)
Disapprove (multiple approvers)
Types of Workflow:
One-Way Workflow (Approver 1--> Approver 2--Approver 3--Etc)
2- Way Workflow ( Approver 1 ---> Approver 2---> Back to Approver 1--> Etc)
REPORTS/ PRINT FORM
Search
Generate
Export to Excel
Export to PDF
EMAIL NOTIFICATION
Static (Content of email cannot be changed)
Dynamic (Content of email cannot be changed)
Examples:
Email Notification to Requestor
Email Notification to Approver
Email Notification to other Identified Recipients
Send Email containing temporary password
ATTACHMENTS
Browse
Attach
Upload
Remove
Download
MODIFICATION HISTORY
Basic (Includes Modified by and Modified Date)
Complex (Includes Changes done per field)
OTHERS
Data Migration
Third Party Integration
Batch Process
COMPATIBILITIES
Browser
Mobile Browser
Mobile Device
Desktop Application
BUSINESS-SPECIFIC LOGIC
Any heavy validation rule?
Is Form content too long?
Are there computations? Formula driven logic?
Are there specific access rights? (ex. Only a specific user can view a certain screen)
Are there performance-specific logic that need to be considered?
Are there security-specific logic that need to be considered?
TESTING ACTIVITIES
Unit Test
Integration Test
System Test
Performance Test
Security Test
DOCUMENTATION
User Manual
Installation Manual
High Level Design
Low Level Design
DB Design
| Deployment Manual | [7 empty] | 5
[9 empty] | 5 | Total MD
[9 empty] | 0.25 | Total MM

## Details (hidden)
|  |  | PM | Design | Devt | Testing | Staging + UAT | Production + Hypercare | Total
Project Management |  |  | #REF!
Specs Gathering
Project Monitoring
Project Reviews
High Level Design
| Detailed HLD |  |  | #REF!
| U/I Design Concept |  |  | #REF!
Low Level Design |  |  |  | #REF!
Program Structure & Pseudocoding
ERD & Database Design
Development
| Development |  |  |  | #REF!
| Unit Testing |  |  |  | #REF!
QA Verification
| Integration Testing |  |  |  |  | #REF!
| System Testing |  |  |  |  | #REF!
| Performance Fine Tuning |  |  |  |  | #REF!
| Security Testing |  |  |  |  | #REF!
Post Implementation
| Staging Release | [5 empty] | #REF!
| UAT Support | [5 empty] | #REF!
| Documentations | [5 empty] | #REF!
| Production Release | [6 empty] | #REF!
| Hypercare Support | [6 empty] | #REF!
|  | Total (ManDays) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Total (ManMonths 20MD 1MM) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Rate (hidden)
NOTE: RATE COLUMN CAN BE ADJUSTED BASED ON THE COMPLEXITY OF THE REQUIREMENT.
|  | Rates | REFERENCE
Project Management |  | 20% | 20%
Specs Gathering
Project Monitoring
Project Reviews
High Level Design
| Detailed HLD | 20% | 20%
| Base HLD Only | 10% | 10%
| U/I Design Concept | 5% | 5%
Low Level Design |  | 20% | 20%
Program Structure & Pseudocoding
ERD & Database Design
Development
| Development | 100% | 100%
| Unit Testing/ POT | 30% | 30%
Unit Testing and QA Verification
| Integration Testing | 20% | 20%
| System Testing | 10% | 10%
| Performance Fine Tuning | 5% | 5%
| Security Testing | 5% | 5%
Deployment / Implementation
| Staging Release | 1% | 1%
| UAT Support | 5% | 5%
| Production Release | 1% | 1%
| Hypercare Support | 5% | 5%
| Documentations | 5% | 5%